## Read Me
SBTDWS 2030 Transformation - First Draft FIC Analysis
Purpose | Working matrix for strategic FIC analysis against the nine Foxglove indicative tasks.
Use | Start with the FIC Matrix sheet for filtering and future build-out. Matrix View mirrors the whiteboard-style row/column layout.
Current maturity | Short planning observations only. Future iterations should add labels, owner, priority, risk, decision/dependency and work package fields.
Created | 2026-05-05 08:01
Amended | 2026-05-05 15:34
Change basis | Incorporated relevant English points from SBTDWS recommendations document into the FIC analysis matrix.

## FIC Matrix
FIC Input | Task ID | Task Heading | Planning Observation | Suggested Work Grouping | Future Label | Owner | Priority | Status | Source / Evidence Note
Organisation / Structure | T1 | Train and validate all-domain operations | SBTDWS requires an endorsed future operating concept before any external ADWC adoption; the future structure should separate training delivery, validation, experimentation, mission rehearsal and enabling support rather than simply rename the existing school. | WG1/WG2/WG6 |  |  |  | Draft
Organisation / Structure | T2 | Hand off CAPDEV cell to Innovation Command | CAPDEV handover needs a defined transition state: permanent, caretaker or full transfer; ambiguity risks orphaning current projects and compromises experimentation possiblities. | WG1/WG2/WG6 |  |  |  | Draft
Organisation / Structure | T3 | Lead tactical experimentation and TTP development | SBTDWS should be the field execution arm for tactical experimentation, with J3 WDC owning governance and doctrine feedback. | WG1/WG2/WG6 |  |  |  | Draft
Organisation / Structure | T4 | Exploit operational trends and lessons | A lessons function or OPEX feeder must be formally embedded; relying on ad hoc course updates will not keep pace with operational change. | WG1/WG2/WG6 |  |  |  | Draft
Organisation / Structure | T5 | Support PG 2030 / Al EMAD POC events | POC events need a single accountable lead, nested in PG 2030 governance; otherwise showcase activity will compete with transformation delivery. | WG1/WG2/WG6 |  |  |  | Draft
Organisation / Structure | T6 | Enhance Hameem mission rehearsal facility | Hameem requires a dedicated mission rehearsal development workstream with J7 architectural authority and J8 capital planning integration. | WG1/WG2/WG6 |  |  |  | Draft
Organisation / Structure | T7 | Exercise SRO responsibility for SAG 9 | SAG 9 responsibility needs clear split between SRO, training provider, validator and operational command; UW raising construct remains a critical uncertainty. | WG1/WG2/WG6 |  |  |  | Draft
Organisation / Structure | T8 | Exercise SRO responsibility for SAG 10 | SAG 10 requires clarity on whether SBTDWS validates R&CB as a training outcome, an operational effect, or both. | WG1/WG2/WG6 |  |  |  | Draft
Organisation / Structure | T9 | Force-generate IW-trained personnel via PGI | The PGI-SBTDWS split must be formalised: PGI owns individual IW training; SBTDWS builds collective readiness and validation. | WG1/WG2/WG6 |  |  |  | Draft
Personnel | T1 | Train and validate all-domain operations | Requires a core of military instructors, OTs and domain SMEs; current capacity is unable to support all-domain training without allocated J-staff, reach-back SMEs and deliberate use of low-tempo windows for development. | WG2/WG3/WG6 |  |  |  | Draft
Personnel | T2 | Hand off CAPDEV cell to Innovation Command | Existing CAPDEV personnel may need to split between experimentation delivery at SBTDWS and capability development governance under Innovation Command. | WG2/WG3/WG6 |  |  |  | Draft
Personnel | T3 | Lead tactical experimentation and TTP development | Needs a small experimentation cell able to design serials, capture data, run AARs and translate findings into TTP recommendations. | WG2/WG3/WG6 |  |  |  | Draft
Personnel | T4 | Exploit operational trends and lessons | Requires staff with analytical skill, recent operational credibility and authority to challenge stale course content; Ramadan/summer windows should be deliberately programmed for course redesign and lessons integration. | WG2/WG3/WG6 |  |  |  | Draft
Personnel | T5 | Support PG 2030 / Al EMAD POC events | Requires event planners, scenario writers, demonstrators, safety staff, data collectors and communications support without stripping core training delivery. | WG2/WG3/WG6 |  |  |  | Draft
Personnel | T6 | Enhance Hameem mission rehearsal facility | Needs HICON/EXCON staff, scenario designers, LVC technicians, range control, facilities management and CIS support; this is beyond normal instructor manning. | WG2/WG3/WG6 |  |  |  | Draft
Personnel | T7 | Exercise SRO responsibility for SAG 9 | Requires UW-experienced instructors, OTs, planners, linguists/culture SMEs and personnel selected through PGI/IWTC pipeline. | WG2/WG3/WG6 |  |  |  | Draft
Personnel | T8 | Exercise SRO responsibility for SAG 10 | Requires SMEs in partner-force training, civil-military engagement, resilience, capacity building and assessment, not only desert warfare instructors. | WG2/WG3/WG6 |  |  |  | Draft
Personnel | T9 | Force-generate IW-trained personnel via PGI | Requires nominated personnel streams, selection standards, attendance forecasting and return-to-unit utilisation plans. | WG2/WG3/WG6 |  |  |  | Draft
Collective Training Pathway | T1 | Train and validate all-domain operations | Requires a codified pipeline from individual qualification to collective validation and FE@R reporting, otherwise all-domain training remains a set of disconnected courses. | WG3/WG6/WG7 |  |  |  | Draft
Collective Training Pathway | T2 | Hand off CAPDEV cell to Innovation Command | CAPDEV outputs should only enter training once validated through a formal experimentation-to-adaptation pathway. | WG3/WG6/WG7 |  |  |  | Draft
Collective Training Pathway | T3 | Lead tactical experimentation and TTP development | Experimentation must be deliberately linked to training design, otherwise TTPs will be demonstrated but not institutionalised. | WG3/WG6/WG7 |  |  |  | Draft
Collective Training Pathway | T4 | Exploit operational trends and lessons | Lessons must drive course review, validation criteria and scenario updates on a routine cycle, not as occasional post-deployment anecdotes. | WG3/WG6/WG7 |  |  |  | Draft
Collective Training Pathway | T5 | Support PG 2030 / Al EMAD POC events | POC events should demonstrate capability progression against standards, not become disconnected technology displays. | WG3/WG6/WG7 |  |  |  | Draft
Collective Training Pathway | T6 | Enhance Hameem mission rehearsal facility | Mission rehearsal should sit at the top of the training continuum and feed validation, FE@R and readiness reporting. | WG3/WG6/WG7 |  |  |  | Draft
Collective Training Pathway | T7 | Exercise SRO responsibility for SAG 9 | Mission rehearsal should sit at the top of the training continuum and feed validation, FE@R and readiness reporting; validation outputs must include evidence-based findings and a remediation pathway. | WG3/WG6/WG7 |  |  |  | Draft
Collective Training Pathway | T8 | Exercise SRO responsibility for SAG 10 | Requires a SAG 9 pathway linking PGI individual IW training, SBTDWS collective training, validation serials and Component Command employment; validation must assess, report and recommend remediation against endorsed standards. | WG3/WG6/WG7 |  |  |  | Draft
Collective Training Pathway | T9 | Force-generate IW-trained personnel via PGI | Requires scenarios and validation criteria that test advisory, resilience and capacity-building outcomes rather than tactical activity alone; findings must be evidence-based and linked to remediation or readiness reporting. | WG3/WG6/WG7 |  |  |  | Draft
Major Systems | T1 | Train and validate all-domain operations | All-domain training depends on LVC, C4I, cyber/EMS overlays and instrumentation; SBTDWS cannot self-generate the digital backbone. | WG4/WG5 |  |  |  | Draft
Major Systems | T2 | Hand off CAPDEV cell to Innovation Command | Current CAPDEV projects need portfolio triage: retain for T&E, transfer to PG units, hand off to J8/Innovation Command, or close. | WG4/WG5 |  |  |  | Draft
Major Systems | T3 | Lead tactical experimentation and TTP development | Makhlab 1 needs an operating model that can test UxS, sensors, comms, EW/EMS effects and decision support without over-promising maturity. | WG4/WG5 |  |  |  | Draft
Major Systems | T4 | Exploit operational trends and lessons | A simple lessons capture and reporting system is required before more complex data tooling is pursued. | WG4/WG5 |  |  |  | Draft
Major Systems | T5 | Support PG 2030 / Al EMAD POC events | Makhlab 1 and UxS showcases require reliable demonstrator systems and backup options; immature systems should be framed as experimentation, not capability. | WG4/WG5 |  |  |  | Draft
Major Systems | T6 | Enhance Hameem mission rehearsal facility | Requires instrumentation, EXCON tools, comms, simulation, digital backbone connectivity and data capture aligned to J7 LVC architecture. | WG4/WG5 |  |  |  | Draft
Major Systems | T7 | Exercise SRO responsibility for SAG 9 | Requires instrumentation, EXCON tools, secure comms, simulation, digital backbone connectivity, digital AAR and evidence capture aligned to J7 LVC architecture. | WG4/WG5 |  |  |  | Draft
Major Systems | T8 | Exercise SRO responsibility for SAG 10 | May require information-management, assessment and reporting tools more than platforms; evidence capture will matter for validation credibility. | WG4/WG5 |  |  |  | Draft
Major Systems | T9 | Force-generate IW-trained personnel via PGI | May require information-management, assessment, digital AAR and reporting tools more than platforms; evidence capture will matter for validation credibility. | WG4/WG5 |  |  |  | Draft
Supplies / Logistics | T1 | Train and validate all-domain operations | Repeatable all-domain training will require a controlled training stores model for specialist equipment, batteries, UxS consumables, spares and range support. | WG5/WG8 |  |  |  | Draft
Supplies / Logistics | T2 | Hand off CAPDEV cell to Innovation Command | Handover must include equipment custody, spares, warranties, support contracts and accountability for prototypes and trial systems. | WG5/WG8 |  |  |  | Draft
Supplies / Logistics | T3 | Lead tactical experimentation and TTP development | Tactical experimentation will consume specialist spares and batteries/ consumables and will require rapid repair/replace pathways to maintain tempo. | WG5/WG8 |  |  |  | Draft
Supplies / Logistics | T4 | Exploit operational trends and lessons | Lessons may reveal changing equipment demand; logistics must be able to adjust training stores and consumable forecasts accordingly. | WG5/WG8 |  |  |  | Draft
Supplies / Logistics | T5 | Support PG 2030 / Al EMAD POC events | Event tempo requires deliberate logistics: transport, charging, spares, range stores, accommodation, media support and contingency holdings. | WG5/WG8 |  |  |  | Draft
Supplies / Logistics | T6 | Enhance Hameem mission rehearsal facility | Operating in Hameem at scale will require J4, medical and sustainment owner input covering sustainment funding, maintenance contracts, range consumables, fuel, water, CASEVAC, recovery, transport and communications sustainment. | WG5/WG8 |  |  |  | Draft
Supplies / Logistics | T7 | Exercise SRO responsibility for SAG 9 | UW training may require bespoke stores, low-signature sustainment, role-player support, comms spares and careful inventory control. | WG5/WG8 |  |  |  | Draft
Supplies / Logistics | T8 | Exercise SRO responsibility for SAG 10 | R&CB activities may need training aids, partner-force equipment, translation material, medical/logistics enablers and deployable advisory kits. | WG5/WG8 |  |  |  | Draft
Supplies / Logistics | T9 | Force-generate IW-trained personnel via PGI | Course attendance and subsequent collective training require transport, accommodation, equipment issue and continuity between PGI and SBTDWS. | WG5/WG8 |  |  |  | Draft
Facilities | T1 | Train and validate all-domain operations | Training areas and classrooms must support planning, simulation, rehearsal and validation; Hameem is pivotal but not sufficient alone. | WG5 |  |  |  | Draft
Facilities | T2 | Hand off CAPDEV cell to Innovation Command | No evidence that Innovation Command co-location or facility model is confirmed; SBTDWS should retain minimum T&E workspace until transition is mature. | WG5 |  |  |  | Draft
Facilities | T3 | Lead tactical experimentation and TTP development | Hameem can become the experimentation venue, but only if instrumented and governed; early serials may need manual data capture. | WG5 |  |  |  | Draft
Facilities | T4 | Exploit operational trends and lessons | Planning and after-action spaces should support secure lessons capture, classified discussion where required and scenario redesign. | WG5 |  |  |  | Draft
Facilities | T5 | Support PG 2030 / Al EMAD POC events | Hameem or alternate venues must be event-ready for visitors, safety control, rehearsals and after-action capture. | WG5 |  |  |  | Draft
Facilities | T6 | Enhance Hameem mission rehearsal facility | Current Hameem is a training area, not an enabled mission rehearsal capability; development requires range authority, safety governance, scheduling control, instrumentation approvals, security, LVC integration and phased capital scope control. | WG5 |  |  |  | Draft
Facilities | T7 | Exercise SRO responsibility for SAG 9 | Needs discrete training areas and mission rehearsal environments suitable for UW scenarios; OPSEC, CI, access control and physical/electronic signature management must be built into the facility model. | WG5 |  |  |  | Draft
Facilities | T8 | Exercise SRO responsibility for SAG 10 | Classroom, planning and role-play environments are as important as field areas; Hameem can support integrated validation but not all R&CB training. | WG5 |  |  |  | Draft
Facilities | T9 | Force-generate IW-trained personnel via PGI | PGI facilities deliver the individual course; SBTDWS needs follow-on environments to consolidate and validate collective application. | WG5 |  |  |  | Draft
Support | T1 | Train and validate all-domain operations | Requires J7, J6, J3 WDC and PGI support to avoid SBTDWS becoming an isolated training provider with an inflated title. | WG3/WG4/WG7 |  |  |  | Draft
Support | T2 | Hand off CAPDEV cell to Innovation Command | Requires legal, contracts, J8, STC and Innovation Command support to avoid informal handover of assets and obligations. | WG3/WG4/WG7 |  |  |  | Draft
Support | T3 | Lead tactical experimentation and TTP development | Requires STC, J3 WDC, J6, J8 and operational unit participation; otherwise experimentation remains school-level innovation. | WG3/WG4/WG7 |  |  |  | Draft
Support | T4 | Exploit operational trends and lessons | Requires J2, mission exploitation, threat analysis and operational unit support to feed adversary TTPs, red-team input, lessons and readiness gaps into SBTDWS; J7 can help connect this to readiness reporting. | WG3/WG4/WG7 |  |  |  | Draft
Support | T5 | Support PG 2030 / Al EMAD POC events | Requires PA/media, protocol, safety, J7, J3 WDC, STC and participating units aligned early. | WG3/WG4/WG7 |  |  |  | Draft
Support | T6 | Enhance Hameem mission rehearsal facility | Requires PG HQ, J7, J6, J8, Hameem/range authorities, security/OPSEC/CI and contractor/industry support; SBTDWS cannot build or sustain this independently. | WG3/WG4/WG7 |  |  |  | Draft
Support | T7 | Exercise SRO responsibility for SAG 9 | SOC handover, PGI/IWTC, Component Command, J3/J7 standards, Security/OPSEC/CI and operational unit support are all gating dependencies. | WG3/WG4/WG7 |  |  |  | Draft
Support | T8 | Exercise SRO responsibility for SAG 10 | Requires doctrine, legal/policy, cultural, language, medical and interagency-style support to avoid reducing R&CB to generic training. | WG3/WG4/WG7 |  |  |  | Draft
Support | T9 | Force-generate IW-trained personnel via PGI | Requires PGI/IWTC scheduling, unit release, Component Command demand signal and SBTDWS tracking of qualified personnel. | WG3/WG4/WG7 |  |  |  | Draft
Command & Management | T1 | Train and validate all-domain operations | COMD PG must decide whether ADWC is a true PG-level capability node or a renamed school; the title creates an expectation gap unless domain ownership, dependencies and reporting authorities are confirmed. | WG1/WG8 |  |  |  | Draft
Command & Management | T2 | Hand off CAPDEV cell to Innovation Command | A formal handover authority and decision date are required; otherwise SBTDWS will plan against assumptions rather than direction. | WG1/WG8 |  |  |  | Draft
Command & Management | T3 | Lead tactical experimentation and TTP development | Experimentation trigger, selection, approval, reporting and output ownership must be clear before Makhlab 1 becomes a precedent for informal activity; J3 WDC should own priorities and TTP transfer. | WG1/WG8 |  |  |  | Draft
Command & Management | T4 | Exploit operational trends and lessons | The Steering Committee should mandate a lessons-to-training governance loop and protect honest reporting so deficiencies can be identified without reputational pressure overriding readiness truth. | WG1/WG8 |  |  |  | Draft
Command & Management | T5 | Support PG 2030 / Al EMAD POC events | POC events should be used as decision points for resource allocation and governance, not only as demonstrations for senior visitors. | WG1/WG8 |  |  |  | Draft
Command & Management | T6 | Enhance Hameem mission rehearsal facility | Hameem decisions should be treated as PG-level capital and readiness decisions, with J7 LVC alignment, J6 digital dependency, security requirements and scope control to avoid an unfunded wish list. | WG1/WG8 |  |  |  | Draft
Command & Management | T7 | Exercise SRO responsibility for SAG 9 | The UW unit raising decision must be escalated early; SAG 9 authority must include standards, reporting chain and power to assess, certify or recommend remediation. | WG1/WG8 |  |  |  | Draft
Command & Management | T8 | Exercise SRO responsibility for SAG 10 | Higher HQ must define standards and reporting authority for SAG 10, including whether SBTDWS can assess, report, certify or recommend remediation, otherwise it can only offer advisory judgement. | WG1/WG8 |  |  |  | Draft
Command & Management | T9 | Force-generate IW-trained personnel via PGI | A joint PGI-SBTDWS force generation mechanism is required so IW-trained personnel are employed in the roles they were generated for. | WG1/WG8 |  |  |  | Draft

## Matrix View
FIC Input | T1: Train and validate all-domain operations | T2: Hand off CAPDEV cell to Innovation Command | T3: Lead tactical experimentation and TTP development | T4: Exploit operational trends and lessons | T5: Support PG 2030 / Al EMAD POC events | T6: Enhance Hameem mission rehearsal facility | T7: Exercise SRO responsibility for SAG 9 | T8: Exercise SRO responsibility for SAG 10 | T9: Force-generate IW-trained personnel via PGI
Organisation / Structure | SBTDWS requires an endorsed future operating concept before any external ADWC adoption; the future structure should separate training delivery, validation, experimentation, mission rehearsal and enabling support rather than simply rename the existing school. | CAPDEV handover needs a defined transition state: permanent, caretaker or full transfer; ambiguity risks orphaning current projects and compromises experimentation possiblities. | SBTDWS should be the field execution arm for tactical experimentation, with J3 WDC owning governance and doctrine feedback. | A lessons function or OPEX feeder must be formally embedded; relying on ad hoc course updates will not keep pace with operational change. | POC events need a single accountable lead, nested in PG 2030 governance; otherwise showcase activity will compete with transformation delivery. | Hameem requires a dedicated mission rehearsal development workstream with J7 architectural authority and J8 capital planning integration. | SAG 9 responsibility needs clear split between SRO, training provider, validator and operational command; UW raising construct remains a critical uncertainty. | SAG 10 requires clarity on whether SBTDWS validates R&CB as a training outcome, an operational effect, or both. | The PGI-SBTDWS split must be formalised: PGI owns individual IW training; SBTDWS builds collective readiness and validation.
Personnel | Requires a core of military instructors, OTs and domain SMEs; current capacity is unable to support all-domain training without allocated J-staff, reach-back SMEs and deliberate use of low-tempo windows for development. | Existing CAPDEV personnel may need to split between experimentation delivery at SBTDWS and capability development governance under Innovation Command. | Needs a small experimentation cell able to design serials, capture data, run AARs and translate findings into TTP recommendations. | Requires staff with analytical skill, recent operational credibility and authority to challenge stale course content; Ramadan/summer windows should be deliberately programmed for course redesign and lessons integration. | Requires event planners, scenario writers, demonstrators, safety staff, data collectors and communications support without stripping core training delivery. | Needs HICON/EXCON staff, scenario designers, LVC technicians, range control, facilities management and CIS support; this is beyond normal instructor manning. | Requires UW-experienced instructors, OTs, planners, linguists/culture SMEs and personnel selected through PGI/IWTC pipeline. | Requires SMEs in partner-force training, civil-military engagement, resilience, capacity building and assessment, not only desert warfare instructors. | Requires nominated personnel streams, selection standards, attendance forecasting and return-to-unit utilisation plans.
Collective Training Pathway | Requires a codified pipeline from individual qualification to collective validation and FE@R reporting, otherwise all-domain training remains a set of disconnected courses. | CAPDEV outputs should only enter training once validated through a formal experimentation-to-adaptation pathway. | Experimentation must be deliberately linked to training design, otherwise TTPs will be demonstrated but not institutionalised. | Lessons must drive course review, validation criteria and scenario updates on a routine cycle, not as occasional post-deployment anecdotes. | POC events should demonstrate capability progression against standards, not become disconnected technology displays. | Mission rehearsal should sit at the top of the training continuum and feed validation, FE@R and readiness reporting. | Mission rehearsal should sit at the top of the training continuum and feed validation, FE@R and readiness reporting; validation outputs must include evidence-based findings and a remediation pathway. | Requires a SAG 9 pathway linking PGI individual IW training, SBTDWS collective training, validation serials and Component Command employment; validation must assess, report and recommend remediation against endorsed standards. | Requires scenarios and validation criteria that test advisory, resilience and capacity-building outcomes rather than tactical activity alone; findings must be evidence-based and linked to remediation or readiness reporting.
Major Systems | All-domain training depends on LVC, C4I, cyber/EMS overlays and instrumentation; SBTDWS cannot self-generate the digital backbone. | Current CAPDEV projects need portfolio triage: retain for T&E, transfer to PG units, hand off to J8/Innovation Command, or close. | Makhlab 1 needs an operating model that can test UxS, sensors, comms, EW/EMS effects and decision support without over-promising maturity. | A simple lessons capture and reporting system is required before more complex data tooling is pursued. | Makhlab 1 and UxS showcases require reliable demonstrator systems and backup options; immature systems should be framed as experimentation, not capability. | Requires instrumentation, EXCON tools, comms, simulation, digital backbone connectivity and data capture aligned to J7 LVC architecture. | Requires instrumentation, EXCON tools, secure comms, simulation, digital backbone connectivity, digital AAR and evidence capture aligned to J7 LVC architecture. | May require information-management, assessment and reporting tools more than platforms; evidence capture will matter for validation credibility. | May require information-management, assessment, digital AAR and reporting tools more than platforms; evidence capture will matter for validation credibility.
Supplies / Logistics | Repeatable all-domain training will require a controlled training stores model for specialist equipment, batteries, UxS consumables, spares and range support. | Handover must include equipment custody, spares, warranties, support contracts and accountability for prototypes and trial systems. | Tactical experimentation will consume specialist spares and batteries/ consumables and will require rapid repair/replace pathways to maintain tempo. | Lessons may reveal changing equipment demand; logistics must be able to adjust training stores and consumable forecasts accordingly. | Event tempo requires deliberate logistics: transport, charging, spares, range stores, accommodation, media support and contingency holdings. | Operating in Hameem at scale will require J4, medical and sustainment owner input covering sustainment funding, maintenance contracts, range consumables, fuel, water, CASEVAC, recovery, transport and communications sustainment. | UW training may require bespoke stores, low-signature sustainment, role-player support, comms spares and careful inventory control. | R&CB activities may need training aids, partner-force equipment, translation material, medical/logistics enablers and deployable advisory kits. | Course attendance and subsequent collective training require transport, accommodation, equipment issue and continuity between PGI and SBTDWS.
Facilities | Training areas and classrooms must support planning, simulation, rehearsal and validation; Hameem is pivotal but not sufficient alone. | No evidence that Innovation Command co-location or facility model is confirmed; SBTDWS should retain minimum T&E workspace until transition is mature. | Hameem can become the experimentation venue, but only if instrumented and governed; early serials may need manual data capture. | Planning and after-action spaces should support secure lessons capture, classified discussion where required and scenario redesign. | Hameem or alternate venues must be event-ready for visitors, safety control, rehearsals and after-action capture. | Current Hameem is a training area, not an enabled mission rehearsal capability; development requires range authority, safety governance, scheduling control, instrumentation approvals, security, LVC integration and phased capital scope control. | Needs discrete training areas and mission rehearsal environments suitable for UW scenarios; OPSEC, CI, access control and physical/electronic signature management must be built into the facility model. | Classroom, planning and role-play environments are as important as field areas; Hameem can support integrated validation but not all R&CB training. | PGI facilities deliver the individual course; SBTDWS needs follow-on environments to consolidate and validate collective application.
Support | Requires J7, J6, J3 WDC and PGI support to avoid SBTDWS becoming an isolated training provider with an inflated title. | Requires legal, contracts, J8, STC and Innovation Command support to avoid informal handover of assets and obligations. | Requires STC, J3 WDC, J6, J8 and operational unit participation; otherwise experimentation remains school-level innovation. | Requires J2, mission exploitation, threat analysis and operational unit support to feed adversary TTPs, red-team input, lessons and readiness gaps into SBTDWS; J7 can help connect this to readiness reporting. | Requires PA/media, protocol, safety, J7, J3 WDC, STC and participating units aligned early. | Requires PG HQ, J7, J6, J8, Hameem/range authorities, security/OPSEC/CI and contractor/industry support; SBTDWS cannot build or sustain this independently. | SOC handover, PGI/IWTC, Component Command, J3/J7 standards, Security/OPSEC/CI and operational unit support are all gating dependencies. | Requires doctrine, legal/policy, cultural, language, medical and interagency-style support to avoid reducing R&CB to generic training. | Requires PGI/IWTC scheduling, unit release, Component Command demand signal and SBTDWS tracking of qualified personnel.
Command & Management | COMD PG must decide whether ADWC is a true PG-level capability node or a renamed school; the title creates an expectation gap unless domain ownership, dependencies and reporting authorities are confirmed. | A formal handover authority and decision date are required; otherwise SBTDWS will plan against assumptions rather than direction. | Experimentation trigger, selection, approval, reporting and output ownership must be clear before Makhlab 1 becomes a precedent for informal activity; J3 WDC should own priorities and TTP transfer. | The Steering Committee should mandate a lessons-to-training governance loop and protect honest reporting so deficiencies can be identified without reputational pressure overriding readiness truth. | POC events should be used as decision points for resource allocation and governance, not only as demonstrations for senior visitors. | Hameem decisions should be treated as PG-level capital and readiness decisions, with J7 LVC alignment, J6 digital dependency, security requirements and scope control to avoid an unfunded wish list. | The UW unit raising decision must be escalated early; SAG 9 authority must include standards, reporting chain and power to assess, certify or recommend remediation. | Higher HQ must define standards and reporting authority for SAG 10, including whether SBTDWS can assess, report, certify or recommend remediation, otherwise it can only offer advisory judgement. | A joint PGI-SBTDWS force generation mechanism is required so IW-trained personnel are employed in the roles they were generated for.

## Work Groupings
ID | Work Grouping | Strategic Purpose | Primary FIC Linkage
WG1 | Governance, Authority and Decision Rights | Own the formal decision architecture: SRO authorities, validation authority, J-staff support decision, UW handover construct, standards endorsement and Steering Committee escalations. | Command & Management; Organisation / Structure
WG2 | Structure and J-Staff Enablement | Design the ADWC operating model, function-based structure, organic/reach-back J-staff options and transition sequencing. | Organisation / Structure; Personnel
WG3 | Training, Validation and Standards | Build the course review, standards, OT cadre, assessment integrity, validation serials and FE@R linkages. | Collective Training Pathway; Personnel; Support
WG4 | Experimentation and CAPDEV Transition | Triage CAPDEV portfolio, establish Makhlab 1 POC model, define J3 WDC trigger/governance and manage Innovation Command transition. | Major Systems; Support; Command & Management
WG5 | Mission Rehearsal, LVC and Hameem | Develop Hameem concept, EXCON/HICON, instrumentation, scenario design, J7 LVC nesting, J6 digital backbone requirements and J8 capital path. | Facilities; Major Systems; Supplies / Logistics
WG6 | SAG 9 / SAG 10 and IW Force Generation | Clarify IW/UW split, SAG 9/10 standards, PGI/SBTDWS pipeline, UW unit raising concept and Component Command employment. | Collective Training Pathway; Personnel; Organisation / Structure
WG7 | Lessons, OPEX and Operational Feedback | Create the mission exploitation-to-training loop and connect J2/threat trends, red-team input, unit lessons and exercise observations to course design, validation criteria and readiness reporting. | Support; Command & Management; Collective Training Pathway
WG8 | Resources, Sustainment and Risk | Translate the FIC gaps into resource asks, sustainment requirements, J4/medical/logistics inputs, security/OPSEC/CI requirements, range authorities, assumptions, dependencies and transition risks for committee control. | Supplies / Logistics; Support; Command & Management

## Tasks
Task ID | Short Heading | Formal Task Summary
T1 | Train and validate all-domain operations | Develop capacity and expertise to train and validate PG FEs to conduct all-domain operations synchronising effects across air, sea, land, cyber, electromagnetic and space domains.
T2 | Hand off CAPDEV cell to Innovation Command | Hand off the existing SBTDWS capability development cell to the new PG Innovation Command.
T3 | Lead tactical experimentation and TTP development | Triggered by J3-led PG WDC, act as PG lead for tactical experimentation, testing operating concepts and developing TTPs before transfer to PG units.
T4 | Exploit operational trends and lessons | Integrate emerging operational trends and PG mission exploitation lessons into training and course design.
T5 | Support PG 2030 / Al EMAD POC events | Starting with Makhlab 1, support proof-of-concept events showcasing key elements of PG transformation.
T6 | Enhance Hameem mission rehearsal facility | Enhance Hameem to provide a world-class mission rehearsal facility for discrete, hyper-realistic pre-deployment training.
T7 | Exercise SRO responsibility for SAG 9 | Develop capacity, knowledge and expertise to exercise SRO responsibility for validating PG FEs' ability to deliver SAG 9, Combined Unconventional Warfare, by 2030.
T8 | Exercise SRO responsibility for SAG 10 | Develop capacity, knowledge and expertise to exercise SRO responsibility for validating PG FEs' ability to deliver SAG 10, Resilience and Capacity Building, by 2030.
T9 | Force-generate IW-trained personnel via PGI | Ensure appropriate personnel attend IW training delivered by PGI so they can be force generated for partnered / combined special forces operations.

## FIC Inputs
FIC Input | Working Definition
Organisation / Structure | How SBTDWS is organised, governed and nested within PG HQ, J7, J3 WDC, Component Command and partner organisations.
Personnel | Numbers, profiles, experience, posting model, instructors, OTs, J-staff support and specialist SMEs.
Collective Training Pathway | Individual-to-collective training progression, validation design, standards, exercises, readiness assurance and feedback loops.
Major Systems | Core platforms, digital systems, LVC architecture, instrumentation, simulation, UxS, data systems and training technology.
Supplies / Logistics | Consumables, spares, training stores, ammunition, mobility, sustainment and life-cycle support for repeatable delivery.
Facilities | Hameem, classrooms, simulation spaces, ranges, field training areas, secure planning spaces and supporting infrastructure.
Support | Engineering, CIS, intelligence, doctrine, legal/policy, medical, administrative, contractor, allied and SME support.
Command & Management | Decision rights, authorities, prioritisation, governance, reporting, risk, benefits, assurance and Steering Committee control.

## Change Log
Priority | Change Area | FIC Location(s) Updated | Amendment Made | Reason
1 | Future operating concept / naming risk | Organisation T1; Command T1 | Added explicit requirement for endorsed future operating concept and controlled ADWC adoption. | Steering Committee needs to resolve role, name, functions and dependencies before external expectation is created.
2 | Validation authority and remediation | Collective T6-T8; Command T7-T8 | Strengthened validation observations to include assess/report/certify/recommend remediation and evidence-based findings. | SAG 9/10 validation is not credible if it remains advisory or lacks a remediation pathway.
3 | J2 / mission exploitation / threat input | Support T4; Work Grouping WG7 | Added J2, threat trends, adversary TTPs, red-team input and mission exploitation linkage. | Keeps scenarios, TTPs, course design and validation standards aligned to operational reality.
4 | Security / OPSEC / CI | Facilities T7; Support T6-T7; Work Grouping WG8 | Added OPSEC, CI, access control and signature-management considerations. | Necessary for discrete mission rehearsal, UW-related training and sensitive activity.
5 | J4 / medical / sustainment | Supplies T6; Work Grouping WG8 | Added J4, medical, CASEVAC, recovery, transport and communications sustainment owners. | Mission rehearsal and validation must exercise support functions, not assume them.
6 | Hameem authorities and governance | Facilities T6; Command T6; Support T6 | Added range authority, safety governance, scheduling control, instrumentation approvals and scope control. | Hameem is a PG-level capital/readiness decision, not merely a facilities upgrade.
7 | Low-tempo development windows | Personnel T1/T4; Read Me | Added Ramadan/summer windows as deliberate development opportunity. | Useful for course redesign, instructor development, simulation planning and experimentation prep.
8 | Digital AAR and evidence capture | Major Systems T6/T8 | Added digital AAR and evidence capture requirements. | Defensible validation depends on evidence management, not just observation.