## Slide 1
SBTDWS → ADWC : IMPLEMENTATION PLAN
Lines of Effort by Phase | Q3 26 – Q4 30
DECISIONS NEEDED FROM PG HQ BY Q4 26: J-Staff: our own or provided? • Is maritime in scope? • Who owns cyber, EMS and space? • Who receives reports? • Who settles PGI disputes? • Is the ADWC name final?
LINE OF EFFORT
Tasks covered
PHASE 1 — DECIDE & AGREE
Q3 26 – Q4 26 GATE: Decisions made
▶
PHASE 2 — CREATE TEAMS & STANDARDS
Q1 27 – Q4 27 GATE: MLOC — Q4 27
▶
PHASE 3 — BUILD FACILITIES & SYSTEMS
Q1 28 – Q4 28 GATE: IOC — Q4 28
▶
PHASE 4 — SUSTAIN & EXPAND
Q1 29 – Q4 30 END STATE: FOC — Q4 30
1. AUTHORITY
& AGREEMENTS
SUPPORTS TASKS 1 – 9
Get the authority to act
Power to pass or fail a unit
Units must attend validation, not volunteer
Decide who approves the standards
Scope and J-Staff decisions (see above)
Agree roles with other headquarters
Written agreement with J7 and PGI
Written agreement with J3 WDC and J8
Component Command agrees to send units
Standards approved and in use
SAG 9, SAG 10 and ADW standards published
Independent checking of results begins
ADWC name confirmed
Work with partner nations
Agreements with partner nations
Our trainers recognised by allied programmes
Review authority and standards each year
2. PEOPLE
& TEAMS
TASKS 1 & 9
Review courses and reorganise
Check every course against 6GW — Q3 26
New SBTDWS structure approved — Q4 26
Bid for Observer Trainer and instructor posts
Create the training teams
Observer Trainer team ready — Q2 27
Military instructors replace contractors — Q4 27
Scenario design team created
Create the exercise control teams
HICON and EXCON teams ready — Q4 28
White Cell, AAR analysts, enemy force team
Joint Fires, cyber and EW specialists
Keep the teams trained and staffed
Career path for validators in place
Instructor training continues every year
Maritime specialists — if in scope
3. STANDARDS
& VALIDATION
TASKS 1, 7 & 8
Write the standards
Draft the ADW validation framework
Send SAG 9 and SAG 10 standards for approval
List required skills for each force element
Test the method below Brigade
Run first validation below Brigade — Q2 27
Publish the Collective Training framework
Train Observer Trainers to approved standard
Validate against SAG 9 and SAG 10
Run a full SAG 9 and SAG 10 validation
Set Joint Fires and counter-drone standards
Publish AAR template and rehearsal framework
Validate units every year
Yearly validation programme — full by Q4 30
Send lessons to J3 WDC and PGI
Review the standards every year
4. EXPERIMENT
& INNOVATE
TASKS 2, 3, 4 & 5
Review projects and plan handover
Review all CAPDEV projects — Q3 26
Agree handover plan to Innovation Command
Design the Makhlab 1 trial framework
Begin experiments under J3 WDC
Run first Makhlab 1 experiment — Q1 27
J3 WDC rules for experiments in use
CAPDEV cell handed to Innovation Command
Demonstrate results and pass on lessons
Makhlab 1 demonstration and drone exercise
Support PG 2030 and AI EMAD trial events
Proven way to pass new TTPs to PG units
Keep improving from experience
Run one experiment every year
Add operational lessons to course design
Innovation Command fully working
5. FACILITIES
& REHEARSAL
TASK 6
Plan and fund Hameem
Hameem plan — what, when and how much
J7 approves the design
Hameem plan approved — Q1 27
Build the simulation and network
Simulation system linked to J7 network
EXCON building and secure network at Hameem
Start building ranges and command post
Open the mission rehearsal facility
Hameem rehearsal facility ready — Q4 28
Urban village, patrol base, cyber and EW ranges
Tracking equipment and AAR analysis tools
Finish building the site
Hameem fully complete — Q4 30
AAR rooms, accommodation, remaining buildings
Maritime training site — if in scope
WE DEPEND ON OTHERS FOR: J7 LVC network • J6 digital network • J3 WDC rules for experiments • PGI course alignment • Hameem funding and approvals
KEY: Italic and underlined = not yet decided, or depends on a PG HQ decision. ▶ = each gate must be passed before the next phase begins. Task numbers = SBTDWS Indicative Tasks (PG 2030, para 3.15b). Task 1 appears in LOE 2 (train) and LOE 3 (validate).