PG 2030 Integrated Development Plan Requirements

Product 3A | Common Planning Standard for Working Groups, Units and Staff Directorates | Version 4

Purpose. This instruction establishes the common requirements for developing every PG2030 Integrated Development Plan. It is task-, Working Group-, Unit- and Staff-agnostic and ensures that all plans are developed, reviewed and managed using one coherent standard.

The purpose of the Integrated Development Plan is not to restate assigned tasks. It is to demonstrate how each approved Line of Effort will progress from its current state through IOC to FOC by 2030.

1. Applicability and Planning Principles

This instruction applies to all PG2030 Integrated Development Plans, regardless of whether the plan owner is a Working Group, Unit or Staff Directorate.

Each plan will be outcome-focused, traceable to approved PG2030 tasking, integrated across required contributors, phased through the PG2030 program timeline, measurable, and owned by a clearly identified Senior Responsible Officer (SRO) and Plan Lead / OIC.

The common plan format is intended to support PG J3 integration, recurring reviews, senior-level decision-making, and coherent program reporting across PG2030.

Standard Planning Logic

The planning process is sequential. Complete the steps in order, then continuously update the plan as decisions, dependencies and evidence mature.

| 1 | Confirm assigned tasks | Concur or recommend changes; obtain PG J3 approval. |
| --- | --- | --- |
| 2 | Establish approved LOEs | Approved tasks become the plan Lines of Effort. |
| 3 | Baseline each LOE | Define where the capability is today and the principal gap. |
| 4 | Define FOC | Describe the required end-of-Phase-3 capability, effect, purpose, scale and conditions. |
| 5 | Define IOC | Work backward from FOC to the minimum usable capability required at the end of Phase 2. |
| 6 | Develop sub-tasks | Identify directed and implied work required to move from baseline to IOC and FOC; brief PG J3. |
| 7 | Set KPIs by phase | Create measurable indicators for Phase 1, Phase 2 and Phase 3. |
| 8 | Build the roadmap | Sequence milestones, contributors, dependencies, constraints and decisions through 2029. |
| 9 | Execute and review | Track performance, update risks/issues, request decisions and refine the plan. |

2. Confirm Assigned Tasks and Establish the Line Of Effort (LOE)

IMMEDIATE ACTION / ASAP: This is the first planning action and should be completed as quickly as practicable. Plan development should not proceed on an assumed task structure that has not been confirmed with PG J3.

Each planning element will review the PG J3-assigned tasks currently associated with its Working Group, Unit or Staff Directorate. For every assigned task, the organization will either:

Formally concur with the task as written; or

Recommend modification, including addition, deletion, consolidation, separation or adjustment of task wording.

PG J3 approval is required before any task change becomes authoritative.

Once approved, those tasks become the plan's Lines of Effort (LOEs).

Control Rule: No organization may independently change its PG2030 LOEs without PG J3 approval. This preserves program-wide ownership, traceability and accountability.

3. Establish the Current State / Baseline for Each Line Of Effort (LOE)

For each approved LOE, provide a concise baseline that identifies:

the capability or condition that exists today;

significant work already completed;

known shortfalls, limitations or constraints; and

the principal gap between the current state and the required 2030 end state.

Keep this concise. The baseline is a planning reference, not a historical narrative. It should be detailed enough to make later KPI progress meaningful.

4. Define the FOC End State for Each Line Of Effort (LOE)

FOC is the destination. For each LOE, describe the condition that must exist by the end of Phase 3 / end of PG2030 for the LOE to be considered fully delivered.

The FOC statement should answer: "What must PG be capable of doing, at what scale, to create what effect, for what purpose, and under what relevant conditions by the end of Phase 3?"

FOC Definition - Minimum Content

Capability / Function - what must be able to be done.

Scale / Echelon - the size or level at which the capability must operate, where applicable (for example: team, company, battalion, battalion task force, brigade(-), brigade, 1-star JTF HQ, 2-star HQ, command-wide enterprise).

Operational Effect - the effect or output the capability must be able to produce.

Purpose - why that capability or effect is required and what operational problem or PG2030 outcome it enables.

Conditions / Integration - the relevant operating conditions, supported/supporting relationships, joint enablers, digital connectivity, readiness state, or other factors necessary for the capability to function.

Sustainability / Institutionalization - where relevant, whether the capability must be trained, resourced, repeatable, sustainable and embedded in normal PG processes.

| Weak FOC Statement | Stronger FOC Statement |
| --- | --- |
| "Complete development of the deployable HQ." | "PG possesses a trained, equipped and validated deployable 1-star JTF HQ capable of commanding a mission-specific force package, integrating required PG and Joint Force enablers, and sustaining continuous operational C2 at the required notice to move." |
| Why weak: describes an activity as complete. | Why stronger: defines capability, echelon/scale, effect, purpose/integration and usable end condition. |

5. Define IOC for Each Line Of Effort (LOE)

Work backward from FOC. Define the Initial Operational Capability required at the end of Phase 2.

IOC is not a percentage of completion. It is the minimum usable and demonstrable capability required before entering Phase 3 optimization and execution.

IOC should use the same logic as FOC, but at the initial operational threshold:

What capability exists at IOC?

At what initial scale or echelon?

What operational effect can it already produce?

For what purpose can it be employed?

Under what known limitations or conditions?

What remains to be optimized, expanded, institutionalized or sustained during Phase 3 to reach FOC?

| IOC Example | FOC Progression |
| --- | --- |
| "One deployable HQ cadre can plan and command a representative mission during a controlled exercise using an initial communications and augmentation package." | "The required headquarters are fully manned, trained, interoperable, sustainable and validated for their assigned mission sets and readiness requirements." |

6. Identify Key Sub-Tasks and Implied Tasks

For each approved LOE, identify the work required to achieve IOC and FOC. This includes:

sub-tasks already directed by PG J3;

implied tasks identified through planning analysis;

enabling actions and coordination requirements;

required approvals and decisions;

testing, experimentation, training and validation activities where applicable; and

fielding, implementation or institutionalization actions.

The planning team is responsible for completing the analysis. Previously identified sub-tasks are a starting point, not a substitute for analysis.

| Approval Gate 1 | Approval Gate 2 |
| --- | --- |
| PG J3 approves the authoritative LOEs. | PG J3 reviews and approves the proposed sub-task structure beneath the LOEs. |

7. Develop KPIs by Phase

A Key Performance Indicator (KPI) is a measurable indicator used to determine whether a plan is making the required progress toward IOC and FOC. A KPI is not simply a task, meeting, discussion, or statement that work is "ongoing." It should allow a reviewer to determine objectively whether the required condition has been achieved, is on track, or is not on track.

A useful KPI should normally contain:

a specific measure - what is being measured;

a target or threshold - the required result;

a due date or phase - when the target must be achieved;

an accountable owner - who is responsible for driving the result;

an evidence source - the data, approval, demonstration, document or event used to confirm progress, where known; and

a status method - for example On Track / At Risk / Off Track, percentage against a defined denominator, or achieved / not achieved.

Rule: If the KPI cannot be objectively assessed, it is probably too vague.

| Phase | Planning Focus | What KPIs Should Demonstrate |
| --- | --- | --- |
| Phase 1 - Analysis, Review & Decision | Understand, design, baseline, decide and approve. | Required analyses, designs, authorities, baselines and decisions are completed and approved. |
| Phase 2 - Experimentation & Adjustment | Develop, test, demonstrate, exercise and refine. | The capability reaches the defined IOC threshold and known deficiencies are being corrected. |
| Phase 3 - Optimization & Execution | Scale, institutionalize, sustain, mature and validate. | The capability reaches the defined FOC condition and can be sustained as an enduring PG capability. |

Illustrative KPI Examples

| Example Area | Weak / Superfluous | Measurable KPI | Why Better |
| --- | --- | --- | --- |
| Deployable HQ | "Conduct HQ training." | "By end of Phase 2, the designated HQ cadre completes two command-post exercises and demonstrates all approved core battle-rhythm functions to the agreed IOC assessment standard." | Defines quantity, timing and observable result. |
| Digital capability | "Improve connectivity." | "By Phase 2 IOC, 100% of designated deployable command posts can exchange the approved operational data set over the defined deployable network during a representative exercise." | Defines users, output, threshold and context. |
| Personnel | "Improve manning." | "By end of Phase 1, 100% of critical billets have approved SQEP criteria and a baseline of authorized, assigned and qualified personnel; by IOC, at least 90% of designated critical billets are filled by qualified personnel." | Uses a denominator and separates baseline from performance. |
| Training / readiness | "Increase readiness." | "By IOC, each designated force element completes the required validation event and closes all critical deficiencies within the approved remediation timeline." | Links readiness to a defined event and closure standard. |
| Concept / policy | "Finalize the concept." | "By the Phase 1 decision point, the concept is approved by the designated authority and all unresolved decision points are either closed or formally accepted as residual issues." | Measures approval and unresolved decisions, not drafting activity. |

Minimum KPI data in the plan: KPI | Target / Threshold | Phase / Due Date | Responsible Owner | Evidence / Data Source (if known) | Status

8. Confirm Membership and Required Contributions

For Working Groups, confirm current membership and recommend additions or removals as required. For Unit and Staff plans, identify the supporting organizations required to deliver the LOEs.

Do not only list participants. State exactly what is required from each member or supporting organization, including the expertise, information, authority, access or deliverable they must provide.

| Organization / Representative | Required Contribution |
| --- | --- |
| Weak entry: "J1 representative" | Does not explain why that person is needed or what they must provide. |
| Stronger example: Personnel staff representative | Able to provide authoritative information on authorized and assigned strength, billet structures, SQEP requirements, career pipelines and personnel-policy constraints; can discuss applicable authorities and options; and has access to PG J1 leadership for rapid clarification or decision-making when required. |

9. Identify Dependencies

Identify dependencies on other Working Groups, Units, Staff Directorates, MOD / Joint Force organizations, external programs, approvals or decisions. A dependency is something another owner must deliver, decide or make available before your LOE can progress as planned.

Dependencies must be specific. Describe what is required, from whom, by when, and what happens if it is late.

| Dependency | Provider | Required Output | Required By | Impact if Delayed |
| --- | --- | --- | --- | --- |
| Weak: "Dependent on Digital Spine" | Digital capability owner | Not specified | Not specified | Not specified |
| Deployable 1-star JTF HQ integration | Digital Spine / J6 capability owner | Approved deployable network architecture, required applications/data services, security/access standards and connectivity package needed for the HQ to operate | Before integrated HQ command-post testing in Phase 2 | HQ cannot conduct representative integrated C2 testing or reach its IOC threshold on schedule |

10. Identify Challenges, Gaps, Obstacles and Constraints

Describe the principal barriers to delivery, ideally by phase. These may include manpower / SQEP, policy, authority, equipment, infrastructure, training, funding, digital connectivity, contracts, doctrine, security, Joint Force enablers, external approvals or time.

| Issue | Phase Affected | Impact | Mitigation / Assistance Required |
| --- | --- | --- | --- |
| Describe the challenge / gap | 1 / 2 / 3 | Effect on delivery / IOC / FOC | Action, support or decision required |

11. Identify the Senior Responsible Officer (SRO) & Plan Lead / OIC by Name

Senior Responsible Officer (SRO). The SRO is the senior officer ultimately accountable for successful delivery of the plan, program or capability. The SRO provides strategic direction, ensures governance and assurance, owns major risks and dependencies, resolves senior-level conflicts, secures required support and resources, and represents the plan to senior leadership.

SRO expectations for PG2030 plans include:

set and protect the intended end state and priorities;

approve the plan direction before it is presented upward, within delegated authority;

ensure the plan has the right team, authority and resources to progress;

own major risks, issues and cross-organizational dependencies that cannot be resolved at working level;

engage senior stakeholders and obtain decisions or support when required;

hold the Plan Lead / OIC and contributing organizations accountable for delivery; and

ensure the plan continues to deliver the intended operational benefit rather than simply completing activities.

Plan Lead / OIC. The Plan Lead / OIC manages day-to-day integration and plan development on behalf of the SRO. This person maintains the plan, coordinates contributors, tracks KPIs/milestones/dependencies, prepares reviews, elevates issues early and ensures decisions are translated into action.

Relationship. The SRO is accountable for the outcome; the Plan Lead / OIC is responsible for day-to-day orchestration and delivery management. Supporting members contribute defined outputs but do not dilute the SRO's accountability.

Every plan will identify:

SRO - name and appointment;

Plan Lead / OIC - name and appointment;

Deputy / alternate - where appropriate.

Continuity Expectation: The designated Plan Lead / OIC should normally remain assigned for a minimum of 12 months to preserve accountability, continuity and institutional knowledge.

12. Evidence and Validation - Initial Identification Only

Do not allow uncertainty over validation to delay plan development. At this stage, each plan should provide only an initial indication of how IOC and FOC might ultimately be demonstrated or validated.

Where the method, authority, standard or event has not yet been determined, identify it as TBD. In many cases validation will depend on external organizations, future exercises, approved Operational Performance Standards, technical testing or senior authorities that the plan owner does not control. PG J3 will subsequently assist plan owners in developing an appropriate validation approach.

Acceptable initial entries may include:

Commander approval;

demonstrated during exercise;

tested / fielded capability;

assessment against an approved Operational Performance Standard;

external MOD certification or validation; or

TBD - validation method to be developed with PG J3.

Initial planning expectation: identify the likely evidence or validation concept if known; otherwise mark it TBD and continue planning.

13. Identify Immediate Assistance / Decisions Required

Every plan must explicitly state what assistance or decision is required from PG J3, Commander PG, or higher authority. This is intended to expose obstacles early and allow senior leaders to intervene before they become schedule delays.

decision or approval;

authority or direction;

prioritization or sequencing;

resource allocation;

cross-organizational conflict resolution;

MOD / Joint Force engagement;

approval of organizational, policy or capability changes.

If none is required, state: "None at this time."

14. Develop the PG2030 Roadmap and Major Milestones

Once the LOEs, sub-tasks, baseline, IOC, FOC and KPIs are defined, place the major delivery activity onto a roadmap aligned to the three PG2030 phases. The phase boundaries below are program-level planning assumptions and remain tentative until formally directed otherwise.

| Phase | Starts | Ends | Planning Meaning |
| --- | --- | --- | --- |
| Phase 1 - Analysis, Review & Decision | 12 Feb 2026 - issuance of Paper 2 | Tentatively by 31 Dec 2026 - approval of Integrated Development Plans by Commander PG | Define and approve the plan: LOEs, baseline, FOC, IOC, sub-tasks, KPIs, contributors, dependencies, major gaps and decisions. |
| Phase 2 - Experimentation & Adjustment | Approval of the Integrated Development Plans | Tentatively 30 Jun 2028 - Initial Operational Capability (IOC) | Implement, test, exercise, demonstrate and adjust the capability until the defined IOC threshold is achieved. |
| Phase 3 - Optimization & Execution | IOC - tentatively 30 Jun 2028 | Tentatively 31 Dec 2029 - Full Operational Capability (FOC) | Optimize, scale, institutionalize, sustain and complete the capability until the defined FOC end state is achieved. |

The roadmap should show sequencing, not every minor action. Show the milestones and dependencies that determine whether each LOE can move from baseline to IOC and then FOC. More detailed schedules may be developed beneath the Integrated Development Plan when required.

15. Maintain Challenges, Risks, Issues, Dependencies and Decisions

These categories are related but are not interchangeable. Using the correct category helps PG J3 understand whether the plan has a current problem, a future threat, a required external input, or a decision that senior leadership must make. Plan owners should update these items during recurring reviews and elevate those that threaten phase KPIs, IOC, FOC or critical milestones.

Challenge / Gap: A known condition, deficiency or limitation that makes delivery harder. It may be internal or external and may require mitigation, resourcing or design change.

Risk: An uncertain future event or condition that may occur and negatively affect delivery. Risks should include likelihood, impact and mitigation where practical.

Issue: A problem that is already occurring. Issues require action, ownership and, when necessary, escalation.

Dependency: An output, decision, capability, resource or contribution that another owner must provide for the plan to progress as intended.

Decision: A choice, approval or direction required from an authority to resolve uncertainty, select a course of action or enable further progress.

| Category | Key Question | Required Management Response |
| --- | --- | --- |
| Challenge / Gap | What condition is making delivery harder? | Describe impact and mitigation / assistance required. |
| Risk | What might happen? | Assess, mitigate, monitor and assign an owner. |
| Issue | What is already happening? | Act now, assign an owner, and escalate if required. |
| Dependency | What do I need from another owner, and by when? | Specify provider, output, date and impact if late. |
| Decision | What senior choice is required? | State the decision needed, by whom and by when. |

16. Progress and Review Requirements

The Integrated Development Plan is a living execution document and will form the basis for recurring PG2030 reviews. Plan owners must be prepared to update and brief:

current phase and overall status;

KPI progress;

milestone progress;

significant achievements;

delays or slippage;

new or changing risks and issues;

dependency changes;

decisions / assistance required; and

next major actions.

17. PG J3 Planning Review Standard

A plan is ready for PG J3 review when it can clearly answer the following questions:

What are the approved LOEs?

Where are we now?

What does FOC look like by the end of Phase 3?

What must exist at IOC by the end of Phase 2?

What work must be completed underneath each LOE?

What measurable outcomes must be achieved in each phase?

Who must contribute, and what is required from them?

What dependencies, challenges, risks and issues may affect delivery?

Who is accountable by name?

What decisions or assistance are required now?

End State for Product 3A: Every PG2030 planning element uses the same disciplined method to convert approved tasks into executable, phased and measurable Integrated Development Plans.

ANNEX A - PG2030 INTEGRATED DEVELOPMENT PLAN: SIMPLIFIED PLANNING FLOW

Use this page as the quick-reference planning sequence. Detailed requirements remain in the main body.

READ THE PLANNING FLOW FROM RIGHT TO LEFT

| 7 SET KPIs BY PHASE Measurable targets for Phases 1-3 | 6 DEVELOP SUB-TASKS Directed + implied work PG J3 APPROVAL | 5 DEFINE IOC Minimum usable capability at end Phase 2 | 4 DEFINE FOC Capability + scale + effect + purpose + conditions | 3 BASELINE Current capability + gap | 2 ESTABLISH LOEs Approved tasks become LOEs | 1 CONFIRM TASKS Concur or recommend changes PG J3 APPROVAL |
| --- | --- | --- | --- | --- | --- | --- |
| ↓ CONTINUE TO STEP 8 AT FAR RIGHT | ← | ← | ← | ← | ← | ← |
| 14 EXECUTE & REVIEW Track KPIs, milestones, dependencies and decisions | 13 SENIOR ASSISTANCE Decisions / direction / resources required | 12 INITIAL VALIDATION Known approach or TBD - do not delay planning | 11 IDENTIFY GAPS / RISKS / ISSUES Mitigation + owner + escalation | 10 MAP DEPENDENCIES Provider + output + required by + impact if late | 9 DEFINE CONTRIBUTORS Who contributes + exactly what is required | 8 BUILD ROADMAP Milestones + dates + sequencing |
| END PLAN ENTERS RECURRING EXECUTION & REVIEW | ← | ← | ← | ← | ← | ← |

PROGRAM PHASES

| PHASE 3 - OPTIMIZATION & EXECUTION IOC → tentative 31 Dec 2029 Optimize / institutionalize / sustain → FOC | PHASE 2 - EXPERIMENTATION & ADJUSTMENT Plan approval → tentative 30 Jun 2028 Develop / test / refine → IOC | PHASE 1 - ANALYSIS, REVIEW & DECISION 12 Feb 2026 → tentative end-Dec 2026 Paper 2 issuance → Commander PG approval of Integrated Development Plans |
| --- | --- | --- |