# J3 Action Plan — Collective Training, Validation and Mission Rehearsal

Format: J3 Action Plan

Effort type: Main Effort

Status: DRAFT — for Commandant review before tabling to J3

Assumptions flagged, not resolved

Several objectives below depend on Commander decisions that are still PENDING. Each dependent objective is marked with a note naming the decision. This plan is written as if SBTDWS's preferred resolution of each decision holds — if a decision lands differently, the affected objective and its timeline must be revisited.

# 1. Phases of Implementation

| Phase | Period | Capability Gate |
| --- | --- | --- |
| Phase One | Now — Q3 2027 | Foundations: OT cadre stood up, first validation serial conducted, structural reorganisation endorsed |
| Phase Two | Q4 2027 — Q1 2029 | Initial Operating Capability (IOC): Hameem mission rehearsal IOC, validation at scale, OT cadre at FOC |
| Phase Three | Q2 2029 — Q3 2030 | Full Operating Capability (FOC): ADWC validation and mission rehearsal function fully operational |

Phase One combines the PREP and Phase 1 stages of the detailed implementation plan — both are foundational and precede the first capability gate.

# 2. Defining Phased Objectives

## Phase One – 2026/2027

1. Stand up an accredited OT cadre to Initial Operating Capability. Selection board convened Q3 26; OT Phase 1 (Foundation Training) and Phase 2 (Supervised Practice) complete; minimum 8 OTs accredited at Level 2 by Q2 27.

2. Conduct the first validation serial. Company-level serial against SAG 9 or ADW focus, OTs in role, by Q2 27.

Depends on D-03 (PENDING)

This objective assumes the Commandant has pre-committed to backing the OT cadre's first adverse assessment. Without D-03 resolved, OTs will self-censor and the serial will not produce a credible result.

3. Endorse the structural reorganisation. Function-based SBTDWS structure (training delivery / validation / experimentation / mission rehearsal / enabling support) endorsed by Q4 26.

Depends on D-01 and D-07 (PENDING)

Structural endorsement requires the three-wing design to be accepted (D-01) and the J-Staff support model confirmed (D-07). Both are PENDING.

4. Endorse the Hameem development concept. Use cases, capital scope, and J7/J6/J8 dependencies agreed by Q3 27.

## Phase Two – 2028

5. Bring Hameem to mission rehearsal IOC. EXCON operational, instrumentation live, first mission rehearsal serial complete by Q4 28.

6. Grow the OT cadre to Full Operating Capability. 20+ OTs across Levels 1–3, including 4+ Senior OTs, self-sustaining accreditation, by Q2 28.

7. Deliver the thematic exercise year. Three themed validation exercises (Experimentation to Adaptation, UxS Tactical Employment, IW/UW) across 2028.

## Phase Three – 2029/2030

8. Declare ADWC/MDWC Full Operating Capability. Full validation capability (SAG 9 at FOC, SAG 10 operational), Hameem at FOC with full LVC integration, by 2030.

Depends on D-05 and D-06 (PENDING)

Validation authority (can SBTDWS certify / fail / recommend remediation?) and SAG 9/10 standards ownership are both PENDING at Higher HQ / PG HQ level. FOC cannot be meaningfully declared while validation remains advisory only.

9. Deliver routine FE@R contributions to MOD via the J7 programme, 2030.

# 3. Identifying Requirements for Achieving Objectives

Endorse the three-wing structural design and the SBTDWS J-Staff support model (organic / allocated / liaison).

Publish ADW competency profiles and an ADW validation framework (how SBTDWS validates, reports, and escalates).

Recruit, train, and accredit the OT cadre (selection board, Foundation Training, Supervised Practice, formal accreditation boards).

Secure command backing for the OT cadre's authority to fail, formalised in a signed writ.

Commission and fund the Hameem mission rehearsal concept (capital sequence, EXCON infrastructure, instrumentation, J7 LVC integration, J6 digital backbone connectivity).

Secure Higher HQ endorsement of SAG 9 and SAG 10 standards and SBTDWS's validation authority.

Resource the additional personnel requirement (OTs, EXCON cell, HICON, OPFOR cell, scenario design cell — estimated 30–45 above current establishment at FOC).