# J3 Action Plan — SBTDWS Transformation (Combined)

Format: J3 Action Plan — single combined document

Status: DRAFT — for Commandant review before tabling to J3

One document or three?

This combines the three separate J3-format Action Plans into a single document, objectives as sub-sections under each of the three required headings. Use this version where J3 wants one document; use the three separate versions where J3 wants to review or approve each objective independently. Content is identical either way.

Assumptions flagged, not resolved

Objectives below are marked wherever they depend on a Commander decision that is still PENDING: D-01, D-03, D-04, D-05, D-06, D-07, D-08, D-09, D-11. This plan is written as if SBTDWS's preferred resolution of each holds — if a decision lands differently, the affected objective and its timeline must be revisited.

# 1. Phases of Implementation

All three objectives run on the same SBTDWS transformation calendar — the phases below apply across the whole plan, not per objective.

| Phase | Period | Capability Gate |
| --- | --- | --- |
| Phase One | Now — Q3 2027 | Foundations: OT cadre to IOC, first validation serial, structural reorganisation endorsed, experimentation governance operational, course consolidation implemented |
| Phase Two | Q4 2027 — Q1 2029 | Initial Operating Capability (IOC): Hameem mission rehearsal IOC, OT cadre to FOC, thematic exercise year, PGI/IWTC pipeline formalised |
| Phase Three | Q2 2029 — Q3 2030 | Full Operating Capability (FOC): ADWC validation and mission rehearsal at FOC, experimentation programme self-sustaining, course portfolio sustained as steady state |

Effort allocation across the three objectives:

| Objective | Effort Type | Work Groupings |
| --- | --- | --- |
| 1. Collective Training, Validation, and Mission Rehearsal | Main Effort | WG1, WG3, WG5, WG6 |
| 2. Tactical Experimentation | Main Effort | WG4, WG7 |
| 3. Training and Course Management | Supporting Effort | WG3, WG6, WG7 |

Phase One combines the PREP and Phase 1 stages of the detailed implementation plan for all three objectives — both are foundational and precede the first capability gate.

# 2. Defining Phased Objectives

## Phase One – 2026/2027

### Objective 1: Collective Training, Validation and Mission Rehearsal (Main Effort)

1.1. Stand up an accredited OT cadre to Initial Operating Capability. Selection board convened Q3 26; OT Phase 1 (Foundation Training) and Phase 2 (Supervised Practice) complete; minimum 8 OTs accredited at Level 2 by Q2 27.

1.2. Conduct the first validation serial. Company-level serial against SAG 9 or ADW focus, OTs in role, by Q2 27.

Depends on D-03 (PENDING) — Commandant pre-commitment to backing the OT cadre's first adverse assessment.

1.3. Endorse the structural reorganisation. Function-based SBTDWS structure (training delivery / validation / experimentation / mission rehearsal / enabling support) endorsed by Q4 26.

Depends on D-01 and D-07 (PENDING) — three-wing design acceptance and J-Staff support model confirmation.

1.4. Endorse the Hameem development concept. Use cases, capital scope, and J7/J6/J8 dependencies agreed by Q3 27.

### Objective 2: Tactical Experimentation (Main Effort)

2.1. Establish the J3 WDC experimentation governance framework. Trigger, approval, reporting, and TTP transfer process defined by Q3 26; SBTDWS executes, J3 WDC owns priorities and outputs.

Depends on D-11 (PENDING) — formal J3 WDC governance for tactical experimentation not yet decided.

2.2. Establish the SBTDWS experimentation cell. 3–5 personnel in role and operational by Q4 26.

2.3. Deliver the first governed Makhlab 1 PoC serial. UxS focus, data captured, AAR conducted, TTP recommendations drafted, by Q1 27, in partnership with Falcons Brigade.

2.4. Complete the first TTP transfer test. Makhlab 1 recommendations reviewed, refined, and formally handed to J3 WDC for unit adoption by Q2 27.

2.5. Finalise the TEIW Standing Charter (v0.2, FPV as Priority 1) and field the UxS portfolio (land and air) by Q2 27.

### Objective 3: Training and Course Management (Supporting Effort)

3.1. Complete the 6GW training review. Full audit of the course portfolio — retain, consolidate, or close — mapped against ADW requirements, by Q3 26.

3.2. Implement the course consolidation plan. Courses restructured or closed per the PREP-phase review; freed capacity redirected to Objective 1, by Q4 26.

3.3. Launch the instructor development programme. Structured programme running in low-tempo (Ramadan/summer) windows, military instructors improving in priority skill areas, from Q4 26.

3.4. Initiate PGI/IWTC engagement. Define the split — PGI delivers individual IW training, SBTDWS delivers collective application and validation — from Q1 27.

## Phase Two – 2028

### Objective 1: Collective Training, Validation and Mission Rehearsal (Main Effort)

1.5. Bring Hameem to mission rehearsal IOC. EXCON operational, instrumentation live, first mission rehearsal serial complete by Q4 28.

1.6. Grow the OT cadre to Full Operating Capability. 20+ OTs across Levels 1–3, including 4+ Senior OTs, self-sustaining accreditation, by Q2 28.

1.7. Deliver the thematic exercise year. Three themed validation exercises (Experimentation to Adaptation, UxS Tactical Employment, IW/UW) across 2028.

### Objective 2: Tactical Experimentation (Main Effort)

2.6. Deliver the thematic UxS Tactical Employment exercise. Large-scale exercise integrating experimentation and validation, across 2028.

2.7. Stand up the formal lessons exploitation mechanism. Quarterly cycle: exercise observations and operational lessons → course review → TTP refinement → validation criteria update, operational by 2028.

2.8. Establish the Makhlab follow-on serial cadence. Annual or bi-annual governed experimentation serials, expanding UxS scope, from FY28.

2.9. Assess maritime UxS scope and feasibility, 2028.

### Objective 3: Training and Course Management (Supporting Effort)

3.5. Formalise the PGI/IWTC pipeline. MoU or equivalent covering attendance tracking, unit release, collective consolidation at SBTDWS, and return-to-unit utilisation, by 2028.

Depends on D-04 (PENDING) — IW/UW boundary must be defined by Higher HQ before the PGI/SBTDWS split can be finalised.

3.6. Achieve military instructor ownership of all core military skills across priority courses, by 2028.

3.7. Operationalise the lessons integration cycle. Quarterly review — exercise AARs and operational lessons feeding course updates and validation criteria review, by 2028.

Cross-objective duplication risk

Objective 2's “lessons exploitation mechanism” (2.7) and Objective 3's “lessons integration cycle” (3.7) describe overlapping machinery — both are quarterly cycles feeding exercise/operational lessons into course design, TTP refinement, and validation criteria review. Combining the two objectives into one document surfaces this: build one lessons mechanism shared across both, not two. Recommend J7/J2 own a single lessons cycle that both Objective 2 and Objective 3 draw from.

## Phase Three – 2029/2030

### Objective 1: Collective Training, Validation and Mission Rehearsal (Main Effort)

1.8. Declare ADWC/MDWC Full Operating Capability. Full validation capability (SAG 9 at FOC, SAG 10 operational), Hameem at FOC with full LVC integration, by 2030.

Depends on D-05 and D-06 (PENDING) — validation authority and SAG 9/10 standards ownership both PENDING at Higher HQ / PG HQ level.

1.9. Deliver routine FE@R contributions to MOD via the J7 programme, 2030.

### Objective 2: Tactical Experimentation (Main Effort)

2.10. Declare the experimentation programme routine and self-sustaining. TEIW operating at scale across land, air, and (if assessed viable) maritime; TTP transfer to units embedded as standard cycle, by 2030.

Depends on D-09 (PENDING) — CAPDEV → PGIC transition plan not yet decided; TEIW's long-term scope cannot be finalised until this boundary is confirmed.

### Objective 3: Training and Course Management (Supporting Effort)

3.8. Sustain the consolidated, credible course portfolio as steady state, feeding instructor and capacity gains directly into Objective 1, through 2030.

3.9. Embed honest assessment culture. Pass rates reflect genuine standards, not social pressure — sustained as a standing Commandant directive.

# 3. Identifying Requirements for Achieving Objectives

## Cross-cutting (applies to all three objectives)

Endorse the three-wing structural design and the SBTDWS J-Staff support model (organic / allocated / liaison) — gates Objective 1's structural reorganisation (D-01, D-07).

Confirm validation authority and SAG 9/10 standards ownership with Higher HQ / PG HQ (D-05, D-06) — gates Objective 1's FOC declaration.

Define the IW/UW boundary with Higher HQ (D-04) — gates Objective 3's PGI/IWTC pipeline and Objective 1's SAG 9 curriculum design.

Resource the consolidated personnel ask across all three objectives (OTs, EXCON cell, HICON, OPFOR cell, scenario design cell, experimentation cell — estimated 30–45 above current establishment at FOC).

Note the single point of failure: SAG 9/10 SRO, UW raising mission, FDC 5 tactical experimentation lead, and Hameem LVC delivery all sit on SBTDWS without dedicated additional resource.

## Objective 1 — Collective Training, Validation and Mission Rehearsal

Publish ADW competency profiles and an ADW validation framework (how SBTDWS validates, reports, and escalates).

Recruit, train, and accredit the OT cadre (selection board, Foundation Training, Supervised Practice, formal accreditation boards).

Secure command backing for the OT cadre's authority to fail, formalised in a signed writ.

Commission and fund the Hameem mission rehearsal concept (capital sequence, EXCON infrastructure, instrumentation, J7 LVC integration, J6 digital backbone connectivity).

## Objective 2 — Tactical Experimentation

Formalise the J3 WDC experimentation governance framework (trigger, approval, reporting, TTP transfer) in writing.

Confirm SBTDWS's mandate as the PG's field execution arm for tactical experimentation, in writing.

Stand up and resource the experimentation cell (3–5 personnel with serial design, data capture, and TTP writing capacity).

Field the UxS portfolio: FPV drones (Priority 1 per TEIW charter), VTOL UxS, land UxS, data capture systems, simulation capacity.

Negotiate and sign the Makhlab 1 Memorandum of Agreement between J3 WDC and SBTDWS.

Define and confirm the CAPDEV → PG Innovation Command (PGIC) transition boundary.

## Objective 3 — Training and Course Management

Complete the 6GW training review and course consolidation plan (retain / consolidate / close decisions per course).

Map the current military vs. contractor instructor delivery ratio; identify priority skills for military ownership.

Design and run the instructor development programme using low-tempo (Ramadan/summer) windows.

Negotiate and formalise the PGI/IWTC pipeline split (individual IW training vs. collective application and validation).

Issue a Commandant directive establishing honest assessment culture — pass rates reflecting standards, not pressure.

Shared lessons mechanism (Objective 2 §2.7 / Objective 3 §3.7) — design and operationalise as one cycle, not two. See note under Phase Two above.