# J3 Action Plan — Training and Course Management

Format: J3 Action Plan

Effort type: Supporting Effort

Status: DRAFT — for Commandant review before tabling to J3

Assumptions flagged, not resolved

One objective below depends on a Commander decision that is still PENDING.

# 1. Phases of Implementation

| Phase | Period | Capability Gate |
| --- | --- | --- |
| Phase One | Now — Q3 2027 | Foundations: course portfolio reviewed and consolidated, instructor development underway, PGI/IWTC engagement initiated |
| Phase Two | Q4 2027 — Q1 2029 | Scale: PGI/IWTC pipeline formalised, military instructor ownership achieved, lessons integration cycle operational |
| Phase Three | Q2 2029 — Q3 2030 | Consolidate: leaner, credible, military-owned course portfolio sustained as steady state, feeding Objective 1 |

Phase One combines the PREP and Phase 1 stages of the detailed implementation plan. This objective is a Supporting Effort — net direction is to free instructor capacity for Objective 1 (Collective Training, Validation and Mission Rehearsal), not to expand the course portfolio.

# 2. Defining Phased Objectives

## Phase One – 2026/2027

1. Complete the 6GW training review. Full audit of the course portfolio — retain, consolidate, or close — mapped against ADW requirements, by Q3 26.

2. Implement the course consolidation plan. Courses restructured or closed per the PREP-phase review; freed capacity redirected to Objective 1, by Q4 26.

3. Launch the instructor development programme. Structured programme running in low-tempo (Ramadan/summer) windows, military instructors improving in priority skill areas, from Q4 26.

4. Initiate PGI/IWTC engagement. Define the split — PGI delivers individual IW training, SBTDWS delivers collective application and validation — from Q1 27.

## Phase Two – 2028

5. Formalise the PGI/IWTC pipeline. MoU or equivalent covering attendance tracking, unit release, collective consolidation at SBTDWS, and return-to-unit utilisation, by 2028.

Depends on D-04 (PENDING)

The IW/UW boundary must be defined by Higher HQ before the PGI/SBTDWS split can be finalised — without it, this pipeline is being designed against an undefined standard.

6. Achieve military instructor ownership of all core military skills across priority courses, by 2028.

7. Operationalise the lessons integration cycle. Quarterly review — exercise AARs and operational lessons feeding course updates and validation criteria review, by 2028.

## Phase Three – 2029/2030

8. Sustain the consolidated, credible course portfolio as steady state, feeding instructor and capacity gains directly into Objective 1, through 2030.

9. Embed honest assessment culture. Pass rates reflect genuine standards, not social pressure — sustained as a standing Commandant directive.

# 3. Identifying Requirements for Achieving Objectives

Complete the 6GW training review and course consolidation plan (retain / consolidate / close decisions per course).

Map the current military vs. contractor instructor delivery ratio; identify priority skills for military ownership.

Design and run the instructor development programme using low-tempo (Ramadan/summer) windows.

Negotiate and formalise the PGI/IWTC pipeline split (individual IW training vs. collective application and validation).

Issue a Commandant directive establishing honest assessment culture — pass rates reflecting standards, not pressure.

Design and operationalise the lessons integration cycle (exercise AARs and operational lessons feeding course review).